## Tabelle1
Master Topic "Integrating Vision & Multimodal Language Models for Building Footprint Quality Assessment" ¦ Franzelin Patrick
| PW1 | PW2 | PW3 | PW4 | PW5 | PW6 | PW7 | PW8 | PW9 | PW10 | PW11 | PW12 | PW13 | PW14 | PW15 | PW16 | PW17 | PW18 | PW19 | PW20 | PW21 | PW22 | PW23 | PW24 | PW25 | PW26 | PW27 | PW28 | PW29 | PW30 | PW31 | PW32 | PW33 | PW19 | PW20 | PW21 | PW22 | PW23 | PW24 | PW25 | PW26 | PW27 | PW28
| 03.11. - 09.11. | 10.11. - 16.11. | 17.11. - 23.11. | 24.11. - 30.11. | 01.12. - 07.12. | 08.12. - 14.12. | 15.12. - 21.12. | 22.12. - 28.12. | 29.12. - 04.01. | 05.01. - 11.01. | 12.01. - 18.01. | 19.01. - 25.01. | 26.01. - 01.02. | 02.02. - 08.02. | 09.02. - 15.02. | 16.02. - 22.02. | 23.02. - 01.03. | 02.03. - 08.03. | 09.03. - 15.03. | 16.03. - 22.03. | 23.03. - 29.03. | 30.03. - 05.04. | 06.04. - 12.04. | 13.04. - 19.04. | 20.04. - 26.04. | 27.04. - 03.05. | 04.05. - 10.05. | 11.05. - 17.05. | 18.05. - 24.05. | 25.05. - 31.05. | 01.06. - 07.06. | 08.06. - 14.06. | 15.06. - 21.06. | 22.06. - 28.06. | 29.06. - 05.07. | 06.07. - 12.07. | 13.07. - 19.07. | 20.07. - 26.07. | 27.07. - 02.08. | 03.08. - 09.08. | 10.08. - 16.08. | 17.08. - 23.08. | 24.08. - 30.08.
[7 empty] | M1 | [6 empty] | M2 |  |  | M3 | [7 empty] | M4 | [5 empty] | M5 |  |  |  |  | M6 |  |  | M7 |  |  |  | M8
WP1: | bar: PW7; PW14; PW17; PW25; PW31; PW21; PW24; PW28
Literature Review & Concept | bar: PW1 to PW7; PW14; PW17; PW25; PW31; PW21; PW24; PW28
WP2: | bar: PW7; PW14; PW17; PW25; PW31; PW21; PW24; PW28
Environment Setup | bar: PW10; PW18; PW25
WP3:
MLLM Testing | bar: PW11 to PW14
WP4:
Visual Mode Testing | bar: PW14 to PW16
WP5:
Automated Refinement VM+MLLM | bar: PW19 to PW21; PW23 to PW24
WP6:
Fine Tuning Toubleshooting | bar: PW17; PW23 to PW25; PW31 to PW19
[19 empty] | x | [14 empty] | x
WP7:
Evaluation & Application Case | bar: PW25 to PW30
WP8:
Writing | bar: PW7; PW10 to PW12; PW17 to PW18; PW31 to PW26
WP9:
Finalization | bar: PW22 to PW28
[34 empty] | Zeit die für den jeweiligen Working Package vorgesehen ist. | [6 empty] | Gelb bedeutet "Pufferzone".
[34 empty] | Grün: Ok, im Zeitplan Rot: Über dem Zeitplan | [6 empty] | Meilensteine
Fine Tuning Toubleshooting
| M | Beschreibung
| M1 | Concept Pitch approved + Theory draft
| M2 | Visual baseline functioning (SAM)
| M3 | MLLM QA pipeline functional
| M4 | Integrated prototype (full pipeline)
| M5 | Evaluation dataset processed, first results
| M6 | Final thesis submission